## Sheet1
Tasks | Names of people working | Priority | Progress | Detailed Description of progress or issues(if any)
Creating classes for Products and its Manager | Wajahat and Archibald | High | In Progress | Product class is almost done just have to conect with data working on Product Manager class
Creating classes for Categories and its Manager(if required) |  | High |  |  | Not started | High
Creating classes for Stocks and its Manager(if required) |  | High |  |  | In Progress | Medium
Creating classes for Customers and its Manager | Thomas, Yamid | Medium | In Progress | Class Creation done (see src) and manager almost finish (not sure about some functions and it misses the connection with the database) if you can check my code to tell me my mistake… | Completed | Low
Creating classes for Bills and its Manager(if required) | Thomas, Yamid | Medium | In Progress | Class Creation done (see src) and manager almost finish (missing connection with database)
Creating classes for Purchases and its Manager(if required) |  | Medium
Creating classes for Database and its Manager |  | High
UI Design Screens(not using C++) |  | Medium
UI Interfaces(QT) |  | Low