## Sheet1
Tasks | Names of people working | Priority | Progress | Detailed Description of progress or issues(if any)
Creating classes for Products and its Manager | Wajahat and Archibald | High | In Progress | Product class is almost done just have to conect with data working on Product Manager class
Creating classes for Categories and its Manager(if required) |  | High |  |  | Not started | High
Creating classes for Stocks and its Manager(if required) |  | High |  |  | In Progress | Medium
Creating classes for Customers and its Manager |  | Medium |  |  | Completed | Low
Creating classes for Bills and its Manager(if required) |  | Medium
Creating classes for Purchases and its Manager(if required) |  | Medium
Creating classes for Database and its Manager |  | High
UI Design Screens(not using C++) |  | Medium
UI Interfaces(QT) |  | Low